## Slide 1
WEEK 2
SPRINT 2
PL6
QUA

## Slide 2: about us.

## Slide 3: QUA
Hugo Marques
Luís Gonçalves
Rui Reis
Ana Almeida
Viviana Abreu
Maria Alves

## Slide 4: Sprint #2 goals.
• Update the QUA section of the quality manual according to experience and the feedback.
• Perform a formal inspection on the QUA section of the Quality Manual. Provide evidence (process, recordings and outcomes – up to the revised artifact)

## Slide 5: tasks.
 | TASK #1 | TASK #2 | TASK #3 | TASK #4 | TASK #5 | TASK #6
TASK | Task delegation and group leadership | Elaboration of the meeting minutes | Status data gathering from the other units | Weekly presentation | Organization of the tasks and presentation | Update of the QUA section of the QM
OWNER | Hugo Marques | Viviana Abreu | Viviana Abreu Luís Gonçalves | Hugo Marques | Ana Almeida | Full Group
GOAL EFFORT | 30 MINUTES | 1 HOUR | 2 HOURS | 30 MINUTES | 2 HOURS | 1 HOUR
EFFECTIVE EFFORT | 30 MINUTES | 1 HOUR | -- | 30 MINUTES | 2 HOURS | 1 HOUR
STATUS | COMPLETED | COMPLETED | IN PROGRESS | COMPLETED | COMPLETED | IN PROGRESS

## Slide 6: planned tasks.
 | TASK #1 | TASK #2 | TASK #3 | TASK #4 | TASK #5 | TASK #6
TASK | Task delegation and group leadership | Elaboration of the meeting minutes | Status data gathering from the other units | Weekly presentation | Update of the QUA section of the QM | Organization of the tasks and presentation
OWNER | Hugo Marques | Viviana Abreu | Viviana Abreu Luís Gonçalves | Hugo Marques | Full Group | Ana Almeida
GOAL EFFORT | 1 HOURS | 1 HOURS | 2 HOURS | 30 MINUTES | 4 HOURS (each) | 2 HOURS
STATUS | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS

## Slide 7: Metrics.
Number of hours spent: 5
Information documents gathered and analysed: 2
a gathe

## Slide 8: Esforço semanal (Gantt).
Full Group
Ana Almeida
Viviana Abreu
Viviana A. / Luís G.
Hugo Monteiro