## Slide 1
WEEK 4
SPRINT 4
PL6
QUA

## Slide 2: about us.

## Slide 3: QUA
Hugo Marques
Luís Gonçalves
Rui Reis
Ana Almeida
Viviana Abreu
Maria Alves

## Slide 4: Sprint #4 goals.
• Update the QUA section of the quality manual according to experience and the feedback.
• Ensure that all team members are working according the Quality Manual procedures and provide evidence of that.

## Slide 5: last weeks tasks.
 | TASK #1 | TASK #2 | TASK #3 | TASK #4 | TASK #5 | TASK #6 | TASK #7
TASK | Task delegation and group leadership | Elaboration of the meeting minutes | PM - ensure and provide evidence that the MQ is being properly used | Update of the Quality Manual (QUA, TST, ENV) | TST - ensure and provide evidence that the MQ is being properly used | Update the IMP section of the MQ | Organization of the tasks and presentation
OWNER | Hugo Marques | Viviana Abreu | Hugo Marques | Ana Almeida Rui Reis | Viviana Abreu | Luís Gonçalves | Ana Almeida
GOAL EFFORT | 45 MINUTES | 30 MINUTES | 1:30 HOURS | 2 HOURS | 1:30 HOURS | 45 MINUTES | 30 MINUTES
EFFECTIVE EFFORT | 45 MINUTES | 45 MINUTES | 2 HOURS | 2 HOURS | 1 HOURS | 45 MINUTES | 30 MINUTES
STATUS | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED

## Slide 6: planned tasks.
 | TASK #1 | TASK #2 | TASK #3 | TASK #4 | TASK #5 | TASK #6
TASK | Task delegation and group leadership | Elaboration of the meeting minutes | ENV - ensure and provide evidence that the MQ is being properly used | Verify if TST metrics and if they are proceeding according to plan | Organization of the tasks and presentation | Update of the REQ section of the MQ
OWNER | Hugo Marques | Ana Almeida | Viviana Abreu | Luís Gonçalves Rui Reis | Ana Almeida | Hugo Marques
GOAL EFFORT | 30 MINUTES | 30 MINUTES | 1 HOUR | 2 HOURS | 30 MINUTES | 30 MINUTES
STATUS | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS

## Slide 7: Metrics.
Number of hours spent: 7:40h
Information documents created, gathered and analysed: 3

## Slide 8: Esforço semanal.